## Sheet1
Mobilisation Plan | [6 empty] | Legend
Subject | Sub Heading | Target date | Completion date | Key Document | Lead | Status | Activity Status Legend
[6 empty] | (see legend) |  | Complete
Project Team | Project team | [6 empty] | On target
| - Agree team members & share contact details | [6 empty] | Some concerns – deadlines pending
| - Agree project team remit | [6 empty] | Urgent – danger of not achieving
- Agree meeting timetable and venues
- Agree any Sub-Groups (see below) and HR
- Resident involvement strategy (if applicable)
Sub groups (if applicable), i.e.;
IT sub group (integration of systems, Client system access)
Technical sub group (determining products etc)
HR sub group (to monitor TUPE issues)
Social Impact sub group
Environmental Impact sub group
insert more as applicable
Programme | Key dates;
- Issue programme/ programme phases
- Approve contractor’s programme
- Issue Work Order (if applicable)
Contract | - Agree contract details
- Contract signed and stored as required
insert more as applicable
Scope of contract | Agree scope of contract;
- Scope and remit agreed including:
works included and specific exclusions
Expectation of how excluded works are handled
Asbestos incident actions (notifiable & non-notifiable)
insert more as applicable
Service Standards | Service Standards;
Principles agreed; final amendments required.
Approve any changes to service standards
Agree Contractors ‘Code of Conduct’
insert more as applicable
Cost plan | Cost plan to be drawn up and agreed based on Budget, tendered Price Framework and agreed programme
Amendments to be agreed (as appropriate) based on any specification changes etc.
Invoicing arrangements and processes agreed
Cost assurance/control processes finalised
Pricing arrangements and process for variations agreed
insert more as applicable
KPIs | KPI’s agreed – data source, measurement, reporting and responsibility confirmed.
Profit related KPI’s agreed (as applicable)
Performance targets and tolerances to be agreed and what constitutes level of unacceptable performance
Current performance against KPI’s presented for comparison purposes.
insert more as applicable
Specification
Product specification to be agreed.
Performance Specifications applicable for some components (where applicable)
Details of specialist suppliers, links to development and planned programme specifications identified.
Specifications to be reviewed on an on-going basis with review meetings to be set up on a regular basis,
Warranties – determine requirement with applicable products e.g. boilers, windows etc,
insert more as applicable
Supply chain | Supply chain arrangements identified and credentials approved by Contract Administrator
Arrangements with local builders merchants identified and agreed (as applicable)
insert more as applicable
Health and Safety | Agreed to follow / not follow CDM.
Principal Designer appointed
Principal Contractor confirmed
Supplier H&S procedures, Risk Assessment & Method Statements obtained
Construction Phase Plan issued and checked by CA
insert more as applicable
Leaseholders & Service Charged Residents | Consultation process on estimates for Leaseholders agreed (if applicable)
Recharge arrangements for leaseholders and Service Charged Residents agreed (if applicable)
insert more as applicable
Personnel & training
TUPE | TUPE applies/does not apply; Terms incorporated into contract.
Applicable staff identified
Consultation & Interviews completed
Appointment completed
Induction completed
Recruitment completed
insert more as applicable
Communication to affected staff | All staff directly affected have had 1;1 briefings.
Publication/communication organised
insert more as applicable
I.T. and telephony | Establish IT sub group (if applicable)
IT sub Group to produce and circulate action plan
- Client/Contractor interface
- Availability of cost information from contractor’s system to enable client side staff to scrutinise costs breakdown
- Use of SOR job codes – (if applicable)
- Training – details of staff requiring training and give indications of the training requirement.
- CRM (if applicable) processes agreed
- Use of written repair notification and appointment confirmation – template needs setting up
- Telephony –
- Call handling arrangements and software – call queuing arrangements and monitoring including stats
- Switch overs to and from OOH (if applicable)
- Actioning OOH orders raised by third party (if applicable)
- Asbestos Register interface (if applicable)
- Text messaging arrangements (if applicable)
- Identification of leasehold, shared ownership properties and impending RTBs (if applicable)
insert more as applicable
Resident involvement | Identify Resident Monitors (if applicable)
Agree role and responsibility
Communication strategy designed and approved
Information on your web site. (need update)
Client’s Response Team briefed
insert more as applicable
Business Continuity Planning | Business Continuity Plan finalised and published
Testing planned and programmed
Finance | Liaision with finance and IT if required
Contractor to send through list of standard reports available via their operating system
Financial completion and invoicing processes tested and approved
insert more as applicable
Quality Control | Principles agreed as follows; (insert)
- Confirm if Quality control needs to link with performance data and payment.
insert more as applicable
Procedures | List to be issued of existing organisational policies and procedures
Procedures to be agreed for complaints handling
Procedures need to be agreed for addressing defective work
insert more as applicable
Supported Housing/Care | Special considerations (service standards) for supported/ vulnerable tenants agreed
Relevant address list issued
Vulnerable tenants flag on Suppliers system. IT subgroup to clarify if information is transferable from Client system (if applicable)
insert more as applicable
Supplier mobilisation | Location; Office facilities and operational premises to be approved
insert more as applicable
Hand over arrangements from exiting supplier (if applicable) | Works in progress - Status of works ordered pre-termination & not actioned
Handover arrangements for all outstanding works – daily monitoring and weekly review
Branding | Joint branding required? (Vehicles, operative uniforms and ID)
Specialists/Consultants | Confirm use of Client’s asbestos specialist to undertake ongoing surveys and removals.
Launch publicity | External publicity approved (as applicable)
Risk Register | Risk register revised and produced post award
Programme of testing, reporting and updating confirmed
insert more as applicable
Data Security | Handover of data or evidence of agreed disposal from outgoing contractor
Approved data security and control management arrangements of incoming contractor
insert more as applicable
Social Impact | Project social impact strategy in place developed from ITT and contractor's proposals.
Key measures and targets identified with reporting process agreed with Contract Administrator
insert more as applicable
Environmental Impact | Project sustainability strategy in place developed from ITT and contractor's proposals.
Key measures and targets identified with reporting process agreed with Contract Administrator
insert more as applicable